## Test report
Test report
Project Name | Coffee Shop Management System
Stage | Sprint 5
Project Code | 5
Test Environment Setup Description | App
Tester | Lee Huu Quyen
Nguyen Dinh Phi
Than Quang Huy
Tran Nguyen Huu Trong
Test Result | PASS
FAIL
SKIPPED
NOT IMPLEMENTED
No | Testcase ID | Function Name | Sheet Name | Create Date
1 | plS - X | Display Drinks Function | Order | 2023-12-19
2 | LmhT - X | Order Processing Function | Order | 2023-12-19
3 | RP - X | Prepare Drink Function | Preparation | 2023-12-19
4 | VM - X | Cashier Processing Function | Cashier | 2023-12-19
5 | UC - X | Receive Bill Feature | Cashier | 2023-12-19
Note: X is Number

## Display Drinks Function
Module |  | Display Drinks Function
Code |  | plS
Check requirement
Tester |  | Lee Huu Quyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 4 | 1 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 4 | 1 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | plS - 1 | Display Drinks Function | Display Drinks Function | System is operational | Open the Order section |  | List of drinks with prices is displayed | 2023-12-19 | PASS |  | PASS | Lee Huu Quyen
2 | plS - 2 | Display Drinks Function | Confirm that the displayed drinks are updated when new drinks are added | New drinks are added to the system | Open the Order section |  | The updated list of drinks, including the newly added ones, is displayed. | 2023-12-19 | PASS |  | PASS | Lee Huu Quyen
3 | plS - 3 | Display Drinks Function | Validate that the prices of the drinks are correctly displayed | The system is operational | Open the Order section |  | Prices of each drink match the predefined values | 2023-12-19 | PASS |  | PASS | Lee Huu Quyen
4 | plS - 4 | Display Drinks Function | Ensure that the display is responsive to changes in drink availability | Drinks are marked as unavailable | Open the Order section |  | Unavailable drinks are clearly indicated in the display | 2023-12-19 | FAIL |  | FAIL | Lee Huu Quyen
5 | plS - 5 | Display Drinks Function | Verify that the display is user-friendly and easy to navigate. | The system is operational | Open the Order section |  | The user interface is intuitive, allowing easy selection of drinks | 2023-12-19 | PASS |  | PASS | Lee Huu Quyen

## Order Processing Function
Module |  | Order Processing Function
Code |  | LmhT
Check requirement
Tester |  | Phan Anh Tuan
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 3 | 3 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 3 | 3 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | LmhT - 1 | Order Processing Function | Confirm that diners can successfully place an order | The system is in the Order section, and drinks are available for selection | 1. Select a drink and specify the quantity using the touchscreen 2. Confirm the order |  | The system registers the order, and the chosen drink appears in the preparation queue | 2023-12-19 | PASS |  | PASS | Nguyen Dinh Phi
2 | LmhT - 2 | Order Processing Function | Validate that the system accurately reflects the ordered quantity | The system is in the Order section | 1. Select a drink and specify the quantity using the touchscreen 2. Confirm the order |  | The system records the specified quantity for the ordered drink | 2023-12-19 | PASS |  | PASS | Nguyen Dinh Phi
3 | LmhT - 3 | Order Processing Function | Ensure that diners can easily modify their order before confirmation | The system is in the Order section, and a drink is selected | 1. Change the quantity or deselect the chosen drink 2. Confirm the modified order |  | The system updates the order details based on the modifications | 2023-12-19 | PASS |  | PASS | Nguyen Dinh Phi

## Prepare Drink Function
Module |  | Food Registration Featue
Code |  | RP
Check requirement
Tester |  | Than Quang Huy
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | RP - 1 | Food Registration Featue | Confirm that drinks are prepared correctly by the bartender | An order is placed and appears in the preparation queue | 1.Go to the Preparation section 2. Confirm the preparation of the specified drink |  | The system updates the status of the prepared drink, and the bartender receives a confirmation | 2023-12-19 | PASS |  | PASS | Than Quang Huy
2 | RP - 2 | Food Registration Featue | Validate the system's response when attempting to prepare an already prepared drink | A drink is marked as prepared | 1. Go to the Preparation section 2. Attempt to confirm the preparation of the same drink |  | The system displays a message indicating that the drink is already prepared | 2023-12-19 | PASS |  | PASS | Than Quang Huy
3 | RP - 3 | Food Registration Featue | Confirm that the preparation queue is updated in real-time | An order is placed, and the preparation queue is empty | 1. Place an order 2. Check the Preparation section |  | The newly placed order is immediately visible in the preparation queue | 2023-12-19 | PASS |  | PASS | Than Quang Huy
6 | RP - 6 | Food Registration Featue | Validate that the cashier system can handle different payment methods (cash, card) | The customer is ready to pay, and multiple payment options are available | 1. Go to the Cashier section 2. Enter the table number and process the payment using cash 3. Repeat the process using a card |  | The system accurately processes payments using both cash and card methods | 2023-12-19 | PASS |  | PASS | Than Quang Huy
7 | RP - 7 | Food Registration Featue | Validate that the cashier system generates accurate change amounts | The customer has paid an amount greater than the total bill | 1. Go to the Cashier section 2. Enter the table number and process the payment with excess amount |  | The system calculates the correct change to be returned to the customer | 2023-12-19 | PASS |  | PASS | Than Quang Huy

## Cashier Processing Function
Module |  | Cashier Processing Function
Code |  | VM
Check requirement
Tester |  | Chau Ngoc Huy
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | VM - 1 | Cashier Processing Function | Validate that the cashier can process a customer's payment accurately | The customer has finished drinking, and the order is processed by the bartender | 1. Go to the Cashier section 2. Enter the table number and process the payment |  | The cashier system calculates the correct amount, processes the payment, and updates the sales information | 2023-12-19 | PASS |  | PASS | Chau Ngoc Huy
2 | VM - 2 | Cashier Processing Function | Confirm that the cashier system handles partial payments correctly | The customer indicates an intention to make a partial payment | 1. Go to the Cashier section 2. Enter the table number and process a partial payment |  | The system accurately calculates the remaining amount and updates the sales information | 2023-12-19 | PASS |  | PASS | Than Quang Huy
3 | VM - 3 | Cashier Processing Function | Validate that the cashier system can handle different payment methods (cash, card). | The customer is ready to pay, and multiple payment options are available | 1. Go to the Cashier section 2. Enter the table number and process the payment using cash 3.Repeat the process using a card |  | The system accurately processes payments using both cash and card methods | 2023-12-19 | PASS |  | PASS | Than Quang Huy
4 | VM - 4 | Cashier Processing Function | Confirm that the cashier can apply discounts or promotional offers correctly | The customer is eligible for a discount or promotional offer | 1. Go to the Cashier section 2. Enter the table number and apply the discount or promotional offer |  | The system updates the total amount after applying the discount or promotional offer | 2023-12-19 | PASS |  | PASS | Than Quang Huy
5 | VM - 5 | Cashier Processing Function | Validate that the cashier system generates accurate change amounts | The customer has paid an amount greater than the total bill | 1. Go to the Cashier section 2. Enter the table number and process the payment with excess amount |  | The system calculates the correct change to be returned to the customer | 2023-12-19 | PASS |  | PASS | Than Quang Huy

## Receive Bill Feature
Module |  | Receive Bill Feature
Code |  | UC
Check requirement
Tester |  | Lee Huu Quyen
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 0 | 0 | 1 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 0 | 0 | 1 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | UC - 1 | Receive Bill Feature | Confirm that diners can view the current bill, including ordered drinks and total amount | The customer has placed an order, and the bartender has confirmed drink preparation | 1. Go to the Order section 2. View the current bill |  | The system displays an accurate summary of ordered drinks and the total amount due | 2023-12-19 | NOT IMPLEMENTED |  | NOT IMPLEMENTED | Phan Anh Tuan